## Environment Quick Assessment
AGIOne Platform - Environment Quick Assessment Record
1. Document Information
Project |  | AGIOne Platform
Assessment Date |  | YYYY-MM-DD
Customer or Site
Deployment Type |  | Local deployment / Cloud-native deployment
Environment Type |  | Development / Testing / Production
Assessor
Owner
2. Assessment Goals
1. Confirm whether the target environment can install and run AGIOne.
2. Identify risks before installation (resource, network, package, permission, storage, operations).
3. Produce a clear remediation list with owners and deadlines.
4. Produce a go-live checklist for final installation approval.
3. Deployment Scope
No. | Scope | Local Deployment | Cloud-Native Deployment
1 | Runtime Model | Docker / Docker Compose on physical servers or VMs | Kubernetes, container registry, Ingress, storage, platform components
2 | Common Pattern | All-in-one single node; host-mode multi-node | Existing Kubernetes cluster; AGIOne-managed kube-cluster delivery
3 | Minimum Node Count | Single-node: 1; host-mode multi-node: 4 | Based on cluster design and workload size
4 | Core Verification | Host resources, SSH, Docker, offline bundle, ports, runtime directories | K8s readiness, registry, StorageClass, Ingress, node resources, namespace permissions
4. Quick Verdict Rules
No. | Verdict | Criteria | Action
1 | Pass | All critical prerequisites are satisfied and no blocking risks remain. | Proceed with installation approval.
2 | Conditional Pass | Installation can proceed after controlled remediation or with accepted non-blocking risks. | Track open items in remediation list and confirm risk acceptance.
3 | Blocked | Any critical prerequisite is missing (insufficient nodes, unreachable SSH, missing bundle assets, unavailable storage, or conflicting network CIDR). | Stop installation until the blocking issue is fixed.
Overall Verdict
5. Local Deployment Prerequisites
5.1 Host Resources
No. | Item | Minimum or Recommended Requirement | Assessment Result | Verdict | Notes
1 | CPU | Recommended 8 cores per AGIOne application node
2 | Memory | Recommended 16 GiB per AGIOne application node
3 | Disk | Recommended 200 GiB available for /opt/hyperone
4 | OS | Linux server with stable package/runtime compatibility
5 | User Permission | Root or equivalent privilege to write /opt, install Docker, and manage services
5.2 Single-Node Local Deployment
No. | Check Item | Requirement | Result | Notes
1 | Target Host | One reachable Linux host
2 | Runtime Directory | /opt/hyperone is writable and has enough capacity
3 | Installer Directory | /opt/agione-installer-bundle can be created or overwritten with approval
4 | Offline Python | Bundle provides offline Python or host provides supported Python
5 | Docker Runtime | Docker / Compose exists or can be installed from offline assets
5.3 Host-Mode Multi-Node Local Deployment
No. | Check Item | Requirement | Result | Notes
1 | Node Count | At least 4 machines: 2 application nodes, 1 middleware node, 1 standby database node
2 | Extra Application Nodes | Additional nodes can be treated as extra application nodes
3 | SSH Access | Controller can connect to all nodes through SSH, preferably with passwordless root access
4 | Node IP Stability | Node IPs are fixed during installation and operation
5 | Time Sync | System time is synchronized across all nodes
6 | Runtime Directories | /opt/hyperone, /opt/agione-installer-bundle, /opt/agione-python are writable on every node
7 | Existing Data | Existing /opt/hyperone data has been reviewed, backed up, or approved for cleanup
8 | Database Replication | Primary and standby database nodes are assigned, standby rebuild data-loss risk accepted when required
5.4 Local Network and Ports
No. | Port / Network | Purpose | Requirement | Result | Notes
1 | 22 | SSH operations | Controller can reach all nodes
2 | 18090 | AGIOne Web entry | Client can access the Nginx gateway node
3 | 80 / 8089 | Nginx and job proxy | Not occupied by unmanaged processes
4 | 3306 | MariaDB | Application and standby database nodes can reach the primary database node
5 | 6379 | Redis | Application nodes can reach middleware node
6 | 8848 / 8849 | Nacos | Application nodes can reach Nacos
7 | 9000 / 9001 | MinIO | Application nodes and operators can reach object storage as needed
8 | 9092 | Kafka | Application nodes can reach Kafka
9 | Docker Network | Docker bridge address pools | Address pools must not overlap with customer networks
6. Cloud-Native Deployment Prerequisites
6.1 Kubernetes Cluster
No. | Check Item | Requirement | Result | Notes
1 | Cluster Access | kubectl access is available with the target kubeconfig
2 | Namespace Permission | Operator can create and manage namespaces, workloads, services, secrets, config maps, and ingress resources
3 | Node Readiness | All planned nodes are Ready, schedulable, and stable
4 | Kubernetes Version | Version is confirmed against the AGIOne delivery package compatibility matrix
5 | Resource Quota | Namespace quota and limit ranges can satisfy AGIOne workloads
6 | CNI | Pod-to-Pod and Service networking are healthy; cluster CIDR does not conflict with customer networks
6.2 Registry, Images, and Offline Delivery
No. | Check Item | Requirement | Result | Notes
1 | Container Registry | Registry is reachable from all cluster nodes
2 | Registry Authentication | Credentials are available and can be stored as Kubernetes secrets
3 | Image Import | Offline images can be imported or pushed before deployment
4 | Image Pull Test | A sample workload can pull images successfully
5 | Package Integrity | Bundle checksum verification is completed before installation
6.3 Storage
No. | Check Item | Requirement | Result | Notes
1 | StorageClass | A default or specified StorageClass is available
2 | ReadWriteOnce | Database and middleware persistent volumes can be provisioned
3 | ReadWriteMany | Shared storage is available if required by the selected deployment design
4 | Capacity | Capacity is sized for database, MinIO/object storage, logs, and model artifacts
5 | Backup | Backup and restore policies are defined and tested for stateful components
6.4 Ingress, DNS, and Certificates
No. | Check Item | Requirement | Result | Notes
1 | Ingress Controller | Ingress controller or load balancer is available
2 | Domain Name | Product access domains are planned and resolvable
3 | TLS Certificate | Certificates are prepared if HTTPS is required
4 | External Access | Client networks can reach the AGIOne entry point
5 | Internal Service Access | Internal services can resolve and reach each other
6.5 Observability and Operations
No. | Check Item | Requirement | Result | Notes
1 | Logging | Application, middleware, Kubernetes, and ingress logs are retained
2 | Monitoring | Node, container, workload, database, and storage metrics are observable
3 | Alerting | Critical alerts are configured for resource pressure, service health, and storage capacity
4 | Upgrade Window | Maintenance windows and rollback plans are defined
5 | Operation Account | Operation accounts, audit requirements, and access boundaries are confirmed
7. Shared Checks
No. | Check Item | Requirement | Result | Notes
1 | Network Policy | Required networks, firewall rules, security groups, and routing are confirmed
2 | Time Sync | NTP or equivalent time synchronization is enabled
3 | DNS | Internal and external domain resolution is stable
4 | Proxy | HTTP/HTTPS proxy requirements are confirmed, or no proxy is required
5 | Offline Mode | Internet access policy is clear; offline assets are complete if the environment is isolated
6 | Security Baseline | Antivirus, host hardening, audit, and password policies will not block installation or runtime
7 | Backup and DR | Backup scope, retention, recovery objective, and responsible team are confirmed
8. Risk Register
No. | Risk ID | Risk | Impact | Severity | Owner | Mitigation | Status
1 | R-001 | Insufficient CPU, memory, or disk | Installation failure or unstable runtime |  |  | Add resources or reduce deployment scope after approval.
2 | R-002 | SSH or node connectivity failure | Host-mode multi-node installation cannot continue |  |  | Fix routing, firewall, credentials, or SSH key distribution.
3 | R-003 | Port conflict | Services fail to start or traffic is routed incorrectly |  |  | Release occupied ports or adjust approved ports.
4 | R-004 | Missing or corrupted offline assets | Installation cannot complete or images cannot load |  |  | Rebuild or reacquire the bundle and verify checksums.
5 | R-005 | Existing runtime data not reviewed | Reinstall may overwrite or mix old data |  |  | Backup, clean, or explicitly approve overwrite.
6 | R-006 | Kubernetes storage is not ready | Stateful workloads cannot start or persist data |  |  | Provide tested StorageClass and backup policy.
7 | R-007 | Registry or image pull failure | Cloud-native workload rollout fails |  |  | Validate registry access and image pull secrets.
8 | R-008 | Incomplete DNS, TLS, or external access planning | Users cannot access AGIOne after deployment |  |  | Confirm domain, certificate, load balancer, and routing.
9. Remediation List
No. | ID | Finding | Required Fix | Owner | Due Date | Verification Method | Status
1 | A-001
2 | A-002
3 | A-003
4 | A-004
5 | A-005
6 | A-006
7 | A-007
8 | A-008
10. Installation Approval Checklist
No. | Checklist Item | Required Evidence | Confirmed
1 | Deployment scope is confirmed | Approved deployment scope and module list
2 | Server or cluster resource check is passed | Resource report, df -h, free -h, CPU count, or Kubernetes node report
3 | Network and port check is passed | Connectivity and port check records
4 | Runtime directories or namespaces are ready | Directory permission result or Kubernetes namespace check
5 | Offline or online package strategy is confirmed | Bundle manifest, checksum report, registry import evidence
6 | Existing data handling is approved | Backup record, cleanup approval, or overwrite approval
7 | Backup and rollback plan is ready | Backup plan, rollback steps, responsible team
8 | Operation and monitoring plan is ready | Monitoring, logging, alerting, and support handover records
9 | All high risks are closed or accepted | Risk register sign-off
11. Post-Installation Verification Checklist
No. | Check Item | Local Deployment Evidence | Cloud-Native Deployment Evidence | Confirmed
1 | Installer result | Installation report shows success | Helm/operator/job result shows success, if applicable
2 | Service status | ./agione ps and ./agione health pass | Pods are running and readiness probes pass
3 | Web access | http://<gateway-ip>:18090/modelone/ is reachable | Product domain or Ingress endpoint is reachable
4 | Middleware health | MariaDB, Redis, Nacos, Kafka, and MinIO are healthy | Stateful workloads and services are healthy
5 | Database replication | Primary/standby replication is healthy when enabled | Database HA policy is verified when applicable
6 | Application initialization | Initialization targets are completed | Initialization jobs or migration jobs are completed
7 | Handover package | ./agione handover output is archived | Deployment manifests, kubeconfig scope, and operation docs are archived
12. Final Sign-Off
No. | Role | Name | Decision | Date | Signature
1 | Customer Owner
2 | Delivery Owner
3 | Operations Owner